EAST END REGENTS CANAL HERITAGE TIMETABLE

| MONTH | ACTIVITY | ACTIONS | WHO |
| --- | --- | --- | --- |
| JUNE | Admin | Scope project | CC/JA |
|  | Admin | Complete HLF form | JA |
|  | Admin Time table | - Create timetable for project - Circulate to those involved | CC/JA |
|  | Marketing | - Have press released agreed - Issue press release mid June - Logo in place - Paper flyer - Flyer – electronic distribution | CC/JA CC CC CC CC/All |
|  | Project workers –brief | - Linda Wilkinson (oral history) - Jim Ives (photography) - Jane Smith (Map/design) | CC |
| JUNE-AUGUST | Oral history | Seek and identify interviewees. Minimum 4 interviews completed | CC/LW |
|  | Map | Walk Canal with Map designer Spare boat place existing trip/photo? | CC/JS JA |
|  | Volunteers for research | - Recruit minimum 5 volunteers - Outreach/networking to recruit | CC/All CC/All |
|  | Archives Contact/engage | - Canal Museum (Charlie) - Tower Hamlets Archives - Malcolm - Look at others, if anything e.g. Bishopsgate, London Met, Kew | CC CC CC + Vol |
|  | Stakeholders: | - Talk to Friends, LRC, LBTH, U3A, Old Ford, VPBC - Identify & talk to others e.g. Ragged School Museum | CC/All |
| SEPTEMBER | Archives Training | - Training session (Week 1 or 2) | CC + LW |
|  | Marketing | September 6th: Islington Canal Festival – Friends stall. Seek Potential contributors (oral histories, photos, vols etc) | CC + FoRC |
|  | Community Group trip | September 11th Group trip and boat trip HUC Growing Concerns/Circle Old Ford | CC + JA |
| SEPTEMBER - OCTOBER | Archives Visits | - Visit Canal Museum - Visit TH archives - Others? + internet searches | CC + LW + Vols |
|  | Review progress |  | CC + JA |
| OCTOBER | LCM exhibition | - Hertford Union Canal – exhibition | CC + LCM |
|  | Community Groups | - Identify groups x 2 - September trips | CC JA |
| NOVEMBER-JANUARY | Archives | - More search, including internet. - Sort permissions - Select images | CC + Vol |
|  | Quiz & Map | Review materials and brief/draft | CC |
|  | Community groups | Presentations/focus groups |  |
|  | Oral History | More interviews, minimum of 6 | CC + LW + vols |
|  | Exhibition | Identify/consult on date/s and venue/s Decide | CC CC+JA |
| FEBRUARY- MARCH | Photography workshops | - Select photos for ‘Then and Now’ - Recruit/Firm up with youth groups - Arrange workshops venue/s - Identify cameras | CC + JI |
|  | Review Material/info | - Look at info gathered - Fill gaps - Identify photos for Then and Now | CC + Vol |
|  | Guides | Guides recruitment completed (NB ongoing process from start) | CC/All |
|  | Map | Finalise | CC + JS |
|  | Quiz | - Finalise text/images - Pilot - Get quotes from designer - Get quotes from printer | CC |
| APRIL-MAY | Photography workshops | Run workshops X 2 (NOTE: Easter March 27-30th,BH: May 2nd and May 30th) | CC + JA + JI + Vol |
|  | Quiz/Map | - To designer by April 1st - To printer by end April |  |
|  | Review progress | Plan exhibition and Canal Day | CC + JA |
|  | Exhibition | - Select material - Pull ingredients together - Create |  |
| MAY last or JUNE 1st week | Guides | Training session (NOTE: Easter March 27-30th, May 2nd and May 30th) | CC |
| JUNE – last 2 weeks | Canal Day/ Exhibition/s | Dates and venues? |  |
|  | School Packs | - Talk to LBTH re logistics - Update existing - Distribute electronically | CC + Vol CC CC/All |
| JULY | Debrief/Report/ Planning | Debrief/Planning Distribute materials/disseminate HLF Report | All CC/All CC |
| SEPTEMBER onwards | Marketing | - Disseminate - Islington Canal Festival - Presentations to e.g. ELHS, FoRC | CC CC/FoRC CC |
|  | Exhibition | LCM exhibition on Regent’s Canal TH | CC+LCM |

CC June 15